## Mitul 49
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹
3. Name of Work: E/F work in Costruction of SDO & Tehsil Office building Girwa Udaipur
4. Agreement No.: |  |  | 49/2021-22
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 15/01/2022
7. Stipulated date of Completion: |  |  | 15/04/2023
8. Actual Date of Completion: |  |  | 02/04/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 02/10/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 26
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Electric sub main work at satellite hospital ambamata Udaipur
4. Agreement No.: |  |  | 26/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 17/11/2024
7. Stipulated date of Completion: |  |  | 16/01/2025
8. Actual Date of Completion: |  |  | 10/01/2025
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 10/07/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 75
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Electric Repair and Maintenance work in Residence No J1/3, Judge Commercial Court, Udaipur
4. Agreement No.: |  |  | 75/2021-22
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 20/03/2022
7. Stipulated date of Completion: |  |  | 19/04/2022
8. Actual Date of Completion: |  |  | 25/03/2022
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 25/09/2022
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 13
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Repairing and renovation of 13 rooms of PWD Dak Bungalow (acquired by circuit house)
4. Agreement No.: |  |  | 13/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 30/07/2022
7. Stipulated date of Completion: |  |  | 29/11/2022
8. Actual Date of Completion: |  |  | 29/11/2022
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 29/05/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 30
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Electric repair work in Ist,IIIrd & IV th Type Quarters at Udaipur
4. Agreement No.: |  |  | 30/2021-22
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 11/09/2021
7. Stipulated date of Completion: |  |  | 10/05/2022
8. Actual Date of Completion:
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP:
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 65
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹
3. Name of Work: EF work in class room at Govt SR.S.econdary School at Kotdi (Bilota) District Rajasamand
4. Agreement No.: |  |  | 65/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 18/10/2023
7. Stipulated date of Completion: |  |  | 17/08/2024
8. Actual Date of Completion: |  |  | 07/01/2025
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 07/07/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 79
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Electric Repair and maintenance work in staff toilet at bar association building rajsamand
4. Agreement No.: |  |  | 79/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 18/10/2023
7. Stipulated date of Completion: |  |  | 17/01/2024
8. Actual Date of Completion: |  |  | 17/01/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 17/07/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 27
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Electric Repair and Maintenance work in Administrative Building and Guest house at RNT medical College Campus Udaipur
4. Agreement No.: |  |  | 27/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 10/09/2023
7. Stipulated date of Completion: |  |  | 09/03/2024
8. Actual Date of Completion: |  |  | 15/05/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 15/11/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 86
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹
3. Name of Work: PF and replacement of exisitng lights by LED Flood bulkhead light in Sahelion ki bari Udaipur
4. Agreement No.: |  |  | 86/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 22/03/2023
7. Stipulated date of Completion: |  |  | 21/05/2023
8. Actual Date of Completion: |  |  | 15/05/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 15/11/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 44
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹
3. Name of Work: EF work in meeting hall at Govt. SR. SEC. SCHOOL AT Shishavi Distt-Rajsamand
4. Agreement No.: |  |  | 44/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 12/10/2023
7. Stipulated date of Completion: |  |  | 11/08/2024
8. Actual Date of Completion: |  |  | 11/08/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 11/02/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 8
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹
3. Name of Work: P/f of light luminaire and Electric repair work in old PG hostel (Near Child Hospital) at RNT Medical college Udaipur
4. Agreement No.: |  |  | 8/2021-22
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 09/08/2021
7. Stipulated date of Completion: |  |  | 08/10/2021
8. Actual Date of Completion: |  |  | 10/09/2021
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 10/03/2022
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 16
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹
3. Name of Work: providing of man power for Electric Repair/Maintenance Work in Non Residential Building at Udaipur, FDPAID - 85557
4. Agreement No.: |  |  | 16 /2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 25/08/2023
7. Stipulated date of Completion: |  |  | 24/08/2024
8. Actual Date of Completion: |  |  | 31/08/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 28/02/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 861
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹
3. Name of Work: PF and Replacement of existing lights by LED flood Bulkhead in Sahelion ki bari Udaipur
4. Agreement No.: |  |  | 86/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 22/03/2023
7. Stipulated date of Completion: |  |  | 21/05/2023
8. Actual Date of Completion:
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP:
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 32
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Electric work at various places at MBGH, Udaipur
4. Agreement No.: |  |  | 32/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 13/11/2022
7. Stipulated date of Completion: |  |  | 12/05/2023
8. Actual Date of Completion: |  |  | 02/01/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 02/07/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 48
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Elect Rep and Renovation of Hostel Room in RIPA Udaipur
4. Agreement No.: |  |  | 48/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 12/12/2022
7. Stipulated date of Completion: |  |  | 11/03/2023
8. Actual Date of Completion: |  |  | 10/03/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 10/09/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 29
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Electric repair and maintenance work in various wards Department of Radiodiagosis kitchen at MB Hospital Udaipur
4. Agreement No.: |  |  | 29/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 10/09/2023
7. Stipulated date of Completion: |  |  | 09/03/2024
8. Actual Date of Completion: |  |  | 28/05/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 28/11/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 28
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Electric repair and Maintenace work in RNT Medical College Udaipur
4. Agreement No.: |  |  | 28/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 10/09/2023
7. Stipulated date of Completion: |  |  | 09/03/2024
8. Actual Date of Completion: |  |  | 08/03/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 08/09/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 751
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹
3. Name of Work: E/M work in ACJM Residence at Rajsamand
4. Agreement No.: |  |  | 75/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 19/02/2023
7. Stipulated date of Completion: |  |  | 05/04/2023
8. Actual Date of Completion: |  |  | 26/03/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 26/09/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 51
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Electric Repair Work and Maintenance Work at Dak Bunglow Udaipur
4. Agreement No.: |  |  | 51/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 21/01/2025
7. Stipulated date of Completion: |  |  | 20/03/2025
8. Actual Date of Completion: |  |  | 24/02/2025
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 24/08/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 59
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Upgradation of CCTV Cameras work in EVM/VVPAT store at Faras Khana in Udaipur
4. Agreement No.: |  |  | 59/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 16/01/2023
7. Stipulated date of Completion: |  |  | 16/03/2023
8. Actual Date of Completion: |  |  | 25/03/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 25/09/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Navyug 02
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Navyug Engineering
2. Amount of Deposit: ₹
3. Name of Work: Remaining Fire fighting work in Commercial Court on the Vth Floor of New Court Complex at District Court Campus, Udaipur
4. Agreement No.: |  |  | 02/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 05/06/2022
7. Stipulated date of Completion: |  |  | 04/12/2022
8. Actual Date of Completion:
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP:
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Neha 56
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Neha Electric
2. Amount of Deposit: ₹
3. Name of Work: Electric Repair and Maintenace work in DJ Court Complex at Rajsamand
4. Agreement No.: |  |  | 56/2022-2023
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 09/01/2023
7. Stipulated date of Completion: |  |  | 09/04/2023
8. Actual Date of Completion: |  |  | 24/03/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 24/09/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Neha 08
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Neha Electric
2. Amount of Deposit: ₹
3. Name of Work: E/F work in dev narayan boys 50 Bedded hostel at nathdwara District-Rajsamand
4. Agreement No.: |  |  | 08/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 17/08/2023
7. Stipulated date of Completion: |  |  | 17/05/2024
8. Actual Date of Completion: |  |  | 05/07/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 05/01/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Neha 59
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Neha Electric
2. Amount of Deposit: ₹
3. Name of Work: E/F work in Meeting at Tehsil Deogarh Distt. Rajsamand
4. Agreement No.: |  |  | 59/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 16/10/2023
7. Stipulated date of Completion: |  |  | 15/08/2024
8. Actual Date of Completion: |  |  | 15/08/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 15/02/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Neha 28
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Neha Electric
2. Amount of Deposit: ₹
3. Name of Work: Remaining E/F Work in Girls Common Room at shri Heera Lal Devpura Govt. College Amet Distt Rajsamand
4. Agreement No.: |  |  | 28/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 15/11/2024
7. Stipulated date of Completion: |  |  | 14/03/2025
8. Actual Date of Completion: |  |  | 04/02/2025
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 04/08/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur