## Vikas 20
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: E/f work in Classroom at Govt. Sr. Secondry School Kunthwa Khamnor Rajsamand
4. Agreement No.: |  |  | 20/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 30/09/2022
7. Stipulated date of Completion: |  |  | 29/07/2023
8. Actual Date of Completion: |  |  | 15/02/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 15/08/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 37
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: E/f in Guru Govind Samudaiyk Bhawan DAL Salumber
4. Agreement No.: |  |  | 37/2020-21
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 16/10/2020
7. Stipulated date of Completion: |  |  | 15/10/2021
8. Actual Date of Completion: |  |  | 10/10/2021
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 10/04/2022
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 35
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Electric renovation of Jr. and Sr Girls Hostel building at RNT Medical College Udaipur
4. Agreement No.: |  |  | 35/2021-22
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 05/10/2021
7. Stipulated date of Completion: |  |  | 04/04/2022
8. Actual Date of Completion: |  |  | 03/04/2022
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 03/10/2022
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 39
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Electric Connection work for Govt College Building at Railmagra Rajsamand
4. Agreement No.: |  |  | 39/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 12/12/2022
7. Stipulated date of Completion: |  |  | 11/01/2023
8. Actual Date of Completion: |  |  | 28/12/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 28/06/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 88
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Supply of Electricians for Genral Maintenance in Main Building MBGH Hospital Udaipur
4. Agreement No.: |  |  | 88/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 25/01/2024
7. Stipulated date of Completion: |  |  | 24/01/2025
8. Actual Date of Completion: |  |  | 31/01/2025
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 31/07/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 72
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Electric Repair and Maintenance Work at UppeR.S.ubordinate Quarter Building 12th Battalion RAC Debari Udaipur
4. Agreement No.: |  |  | 72/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 15/02/2025
7. Stipulated date of Completion: |  |  | 30/03/2025
8. Actual Date of Completion: |  |  | 21/03/2025
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 21/09/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 54
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Electrical Wiring work in ADR Court at DJ Court Campus, Udaipur (Capital Head-)
4. Agreement No.: |  |  | 54/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 01/01/2023
7. Stipulated date of Completion: |  |  | 01/03/2023
8. Actual Date of Completion: |  |  | 01/03/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 01/09/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 95
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Electrical Repairing work at Various Court of District headquarter Udaipur
4. Agreement No.: |  |  | 95/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 16/03/2024
7. Stipulated date of Completion: |  |  | 15/04/2024
8. Actual Date of Completion: |  |  | 20/03/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 20/09/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 24
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Electric Repair Work in Govt. Residential Ist and IInd Building Udaipur
4. Agreement No.: |  |  | 24/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 17/11/2024
7. Stipulated date of Completion: |  |  | 16/07/2025
8. Actual Date of Completion: |  |  | 15/01/2025
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 15/07/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 102
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Electric Renovation & Maintenance of Dining Hall & Mess at HCM RIPA Udaipur
4. Agreement No.: |  |  | 102/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 24/03/2024
7. Stipulated date of Completion: |  |  | 23/09/2024
8. Actual Date of Completion: |  |  | 18/12/2025
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 18/06/2026
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 4
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Repairing of 250KVA Transformer at DJ Court Udaipur
4. Agreement No.: |  |  | 4/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 18/06/2022
7. Stipulated date of Completion: |  |  | 17/07/2022
8. Actual Date of Completion: |  |  | 17/07/2022
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 17/01/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 120
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Electric repair and MTC work in Various type lllrd and IVth type resi. Qtr Udaipur
4. Agreement No.: |  |  | 120/2020-21
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 21/03/2021
7. Stipulated date of Completion: |  |  | 20/04/2021
8. Actual Date of Completion: |  |  | 20/04/2021
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 20/10/2021
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 115
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Electric Repair and Mtc in Electric Panel romm at Shri SundeR.S.ingh Bhandari Hospital Chandpol Udaipur
4. Agreement No.: |  |  | 115/2020-21
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 21/03/2021
7. Stipulated date of Completion: |  |  | 04/04/2021
8. Actual Date of Completion: |  |  | 01/04/2021
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 01/10/2021
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 87
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Supply of Electrician for General Maintenance in Trauma Block & Near by Building Udaipur 2023-24
4. Agreement No.: |  |  | 87/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 25/01/2024
7. Stipulated date of Completion: |  |  | 24/01/2025
8. Actual Date of Completion: |  |  | 31/01/2025
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 31/07/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 94
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Remaining Electrification work in Tehsil Building at Kherwada District Udaipur
4. Agreement No.: |  |  | 94/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 16/03/2024
7. Stipulated date of Completion: |  |  | 15/06/2024
8. Actual Date of Completion: |  |  | 01/06/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 01/12/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 21
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Electric Repair Work in Govt. Residential Vth Type Building Udaipur
4. Agreement No.: |  |  | 21/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 17/11/2024
7. Stipulated date of Completion: |  |  | 16/07/2025
8. Actual Date of Completion: |  |  | 10/06/2025
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 10/12/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 45
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: AMC of APFC Panel installed DJ Court Campus Udaipur 2020-21
4. Agreement No.: |  |  | 45/2020-21
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 24/10/2020
7. Stipulated date of Completion: |  |  | 23/10/2021
8. Actual Date of Completion: |  |  | 23/10/2021
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 23/04/2022
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 58
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: P/L of HT and LT cable in Public Health Lab at MB Hospital premises, Udaipur
4. Agreement No.: |  |  | 58/2021-22
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 17/01/2022
7. Stipulated date of Completion: |  |  | 16/02/2022
8. Actual Date of Completion: |  |  | 16/02/2022
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 16/08/2022
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 99
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Hiring of Labour for Electrical Mtc of Residential Building Udaipur
4. Agreement No.: |  |  | 99/2019-20
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 21/03/2020
7. Stipulated date of Completion: |  |  | 20/03/2021
8. Actual Date of Completion: |  |  | 20/03/2021
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 20/09/2021
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 02
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Hire Charges of DG and Flood Lights for VIP Visit at Udaipur
4. Agreement No.: |  |  | 02/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 11/05/2022
7. Stipulated date of Completion: |  |  | 10/06/2022
8. Actual Date of Completion: |  |  | 16/05/2022
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 16/11/2022
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 80
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Repair & Maintenance work (LT Cable, electric works) at CJ & JM Court Kherwara, FDPAID - 76185
4. Agreement No.: |  |  | 80/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 07/03/2023
7. Stipulated date of Completion: |  |  | 06/04/2023
8. Actual Date of Completion: |  |  | 30/03/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 30/09/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 211
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: EF work in class room at Govt sR.S.econdary School Khamnore Distt Rajsamand
4. Agreement No.: |  |  | 21/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 30/09/2022
7. Stipulated date of Completion: |  |  | 29/07/2023
8. Actual Date of Completion: |  |  | 29/07/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 29/01/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 23
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Providing of Labour for Day to Day Electric Maintenance Work in Govt. Residential Building Udaipur (IIIrd type and IVth type Quarters 2024-25)
4. Agreement No.: |  |  | 23/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 17/11/2024
7. Stipulated date of Completion: |  |  | 16/05/2025
8. Actual Date of Completion: |  |  | 31/03/2025
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 30/09/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 881
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Electric repair work in govt residential udaipur
4. Agreement No.: |  |  | 88/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 24/03/2023
7. Stipulated date of Completion: |  |  | 30/03/2023
8. Actual Date of Completion: |  |  | 27/03/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 27/09/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 31
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Electric repair and Maintenace work in trauma and blood bank at MBGH campus Udaipur
4. Agreement No.: |  |  | 31/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 13/09/2023
7. Stipulated date of Completion: |  |  | 12/01/2024
8. Actual Date of Completion: |  |  | 10/01/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 10/07/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur