## Vikas 101
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Earthing work and other repair work at excise building at udaipur
4. Agreement No.: |  |  | 101/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 24/03/2024
7. Stipulated date of Completion: |  |  | 23/06/2024
8. Actual Date of Completion: |  |  | 13/06/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 13/12/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 79
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Electric Repair and Maintenance Work at Administrative Building 12th Battalion RAC Debari Udaipur
4. Agreement No.: |  |  | 79/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 20/02/2025
7. Stipulated date of Completion: |  |  | 05/04/2025
8. Actual Date of Completion: |  |  | 23/03/2025
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 23/09/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 05
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: AMC Work of APFC Panel Installed at DJ Court Campus, Udaipur
4. Agreement No.: |  |  | 05/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 31/08/2024
7. Stipulated date of Completion: |  |  | 30/08/2025
8. Actual Date of Completion:
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP:
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 113
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: HTDP structure related work in Mines & Geology Deptt. Udaipur
4. Agreement No.: |  |  | 113/2020-21
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 21/03/2021
7. Stipulated date of Completion: |  |  | 04/04/2021
8. Actual Date of Completion: |  |  | 12/03/2021
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 12/09/2021
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 100
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Electrification of Seating and Prayer Hall (60X40) at Govt Se.Sec. School at Brahmano ka kherwada in Jhadol Distt. Udaipur
4. Agreement No.: |  |  | 100/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 08/04/2023
7. Stipulated date of Completion: |  |  | 07/07/2023
8. Actual Date of Completion: |  |  | 06/07/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 06/01/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 70
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Electric Renovation Work in State Motor Garrage Building Udaipur
4. Agreement No.: |  |  | 70/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 15/02/2025
7. Stipulated date of Completion: |  |  | 14/04/2025
8. Actual Date of Completion: |  |  | 27/03/2025
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 27/09/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 29
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Supply of experienced wireman Electricians for day to day maintenance for MB hospital and its associates building Udaipur
4. Agreement No.: |  |  | 29/2021-22
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 11/09/2021
7. Stipulated date of Completion: |  |  | 10/09/2022
8. Actual Date of Completion: |  |  | 10/09/2022
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 10/03/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 1011
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Electrical maintenance and Upgradation of electric substation in MBGH Udaipur, FDPAID - 77098
4. Agreement No.: |  |  | 101/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 08/04/2023
7. Stipulated date of Completion: |  |  | 07/07/2023
8. Actual Date of Completion: |  |  | 07/07/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 07/01/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 60
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Supply of Electricians for General Maintenance in Main Building MBGH Hospital Udaipur Fy 2025-26
4. Agreement No.: |  |  | 60/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 01/02/2025
7. Stipulated date of Completion: |  |  | 31/01/2026
8. Actual Date of Completion:
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP:
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 17
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Providing of Labour for Day to Day Electric Maintenance Work in Govt. Non Residential Building Udaipur
4. Agreement No.: |  |  | 17/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 25/10/2024
7. Stipulated date of Completion: |  |  | 24/10/2025
8. Actual Date of Completion:
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP:
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 07
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Additional Electrification of Extension of Govt Polytechnic College at Dakshin Vistaar Udaipur
4. Agreement No.: |  |  | 07/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 31/08/2024
7. Stipulated date of Completion: |  |  | 30/10/2024
8. Actual Date of Completion: |  |  | 30/10/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 30/04/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 80
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Electric Repair and Maintenance Work at Gulab Barrack (100 Men) 12th Battalion RAC Debari Udaipur
4. Agreement No.: |  |  | 80/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 20/02/2025
7. Stipulated date of Completion: |  |  | 05/04/2025
8. Actual Date of Completion: |  |  | 20/03/2025
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 20/09/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 55
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Electric repair and Maintenance work of Administrative Building at Police thana Pratap Nagar Udaipur
4. Agreement No.: |  |  | 55/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 21/01/2025
7. Stipulated date of Completion: |  |  | 20/03/2025
8. Actual Date of Completion: |  |  | 10/03/2025
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 10/09/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 32
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Electri repair and maintenance work in Lecture theatre exam Building auditiorium old libary, badminton court at RNT Medical college Udaipur
4. Agreement No.: |  |  | 32/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 13/09/2023
7. Stipulated date of Completion: |  |  | 12/01/2024
8. Actual Date of Completion: |  |  | 12/01/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 12/07/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 34
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Electric Repair and maintenance work of Cardiology and SSH Building at MB Hospital Campus Udaipur
4. Agreement No.: |  |  | 34/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 13/09/2023
7. Stipulated date of Completion: |  |  | 12/01/2024
8. Actual Date of Completion: |  |  | 24/04/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 24/10/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 33
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Electric repair and maintenance work in various hostel (New Junior boys,SR hostel, Intern hostel Nursing Hostel ) at RNT Medical college Udaipur
4. Agreement No.: |  |  | 33/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 13/09/2023
7. Stipulated date of Completion: |  |  | 12/01/2024
8. Actual Date of Completion: |  |  | 10/03/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 10/09/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 44
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Supply of Electricians for general Electric maintenance in Trauma Block & Near by Building Udaipur
4. Agreement No.: |  |  | 44/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 12/12/2022
7. Stipulated date of Completion: |  |  | 11/12/2023
8. Actual Date of Completion: |  |  | 29/12/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 29/06/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 3
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Tender for the work Temporary lighting arrangement work during VIP visit in Udaipur
4. Agreement No.: |  |  | 3/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 03/06/2022
7. Stipulated date of Completion: |  |  | 02/06/2023
8. Actual Date of Completion: |  |  | 09/06/2022
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 09/12/2022
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vikas 97
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vikas Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Electric Repair and Maintenance works at Cardiology Department, SSH , UG/PG girls hostel and GNM lecture hall at RNT Medical College Udaipur-, FDPAID - 77015
4. Agreement No.: |  |  | 97/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 08/04/2023
7. Stipulated date of Completion: |  |  | 07/11/2023
8. Actual Date of Completion: |  |  | 27/10/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 27/04/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vimal 92
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vimal Electricals
2. Amount of Deposit: ₹
3. Name of Work: Providing of Labour for day to day Electric Manitenance Work in Govt. Residential Building at Udaipur
4. Agreement No.: |  |  | 92/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 14/03/2024
7. Stipulated date of Completion: |  |  | 13/11/2024
8. Actual Date of Completion: |  |  | 13/11/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 13/05/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vimal 81
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vimal Electricals
2. Amount of Deposit: ₹
3. Name of Work: Electric work in Science Lab at Vigyan samiti Ashok Nager Udaipur
4. Agreement No.: |  |  | 81/2020-21
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 23/01/2021
7. Stipulated date of Completion: |  |  | 22/07/2021
8. Actual Date of Completion: |  |  | 22/07/2021
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 22/01/2022
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vimal 77
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vimal Electricals
2. Amount of Deposit: ₹
3. Name of Work: Elect rep. work in Non Residential Qtr Udaipur
4. Agreement No.: |  |  | 77/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 19/02/2023
7. Stipulated date of Completion: |  |  | 18/03/2023
8. Actual Date of Completion: |  |  | 18/03/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 18/09/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vimal 96
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vimal Electricals
2. Amount of Deposit: ₹
3. Name of Work: Electric repair work in Judicial quarters at District head quarter Udaipur
4. Agreement No.: |  |  | 96/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 16/03/2024
7. Stipulated date of Completion: |  |  | 15/04/2024
8. Actual Date of Completion: |  |  | 28/03/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 28/09/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vimal 19
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vimal Electricals
2. Amount of Deposit: ₹
3. Name of Work: S/f of Elect Material for Mtc of Various Govt Resi Building Udaipur
4. Agreement No.: |  |  | 19/2021-22
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 15/08/2021
7. Stipulated date of Completion: |  |  | 14/06/2022
8. Actual Date of Completion: |  |  | 10/06/2022
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 10/12/2022
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Vimal 87
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Vimal Electricals
2. Amount of Deposit: ₹
3. Name of Work: Electric repair work of Government residential Quarter l/132(Judicial Magistrate Family Court no-1) at Pratap Nagar Distt Udaipur
4. Agreement No.: |  |  | 87/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 24/03/2023
7. Stipulated date of Completion: |  |  | 30/03/2023
8. Actual Date of Completion: |  |  | 26/03/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 26/09/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Total: ₹
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur