## Abhinav 104
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Abhinav Engineering and Suppliers
2. Amount of Deposit: ₹
3. Name of Work: E/F work in Guru Govind singh samudayik bhavan in sayara panchayat samiti Udaipur
4. Agreement No.: |  |  | 104/2020-21
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 11/03/2021
7. Stipulated date of Completion: |  |  | 10/03/2022
8. Actual Date of Completion: |  |  | 13/05/2022
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 13/11/2022
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 79812 Date 31-03-2023 |  | SD | 1022
Voucher No.- 79812 Date 31-03-2023 |  | MD-V | 30000
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Arun 107
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Arun Electricals
2. Amount of Deposit: ₹
3. Name of Work: E/f work in Shikshak Awas Kotra
4. Agreement No.: |  |  | 107/2013-14
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 14/10/2013
7. Stipulated date of Completion: |  |  | 13/04/2015
8. Actual Date of Completion: |  |  | 03/07/2019
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 03/01/2020
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 83070 Date 31-03-2024 |  | SD | 59096
Voucher No.- 83070 Date 31-03-2024 |  | MD-V | 50000
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Arun 133
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Arun Electricals
2. Amount of Deposit: ₹
3. Name of Work: E/F in Lecture theatre Block RNT Medical College Udaipur
4. Agreement No.: |  |  | 133/2014-15
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 26/02/2015
7. Stipulated date of Completion: |  |  | 25/08/2016
8. Actual Date of Completion: |  |  | 20/02/2020
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 20/08/2020
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 39086 Date 13-10-2023 |  | SD | 158676
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Arun 14
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Arun Electricals
2. Amount of Deposit: ₹
3. Name of Work: E/F work in Govt College building at Kumbhalgarh Rajsamand
4. Agreement No.: |  |  | 14/2019-20
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 15/08/2019
7. Stipulated date of Completion: |  |  | 14/11/2020
8. Actual Date of Completion: |  |  | 23/02/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 23/08/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 35078 Date 22-09-2023 |  | SD | 170938
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Arun 20
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Arun Electricals
2. Amount of Deposit: ₹
3. Name of Work: E/f work in Meeting Hall at SDM Office Kumbhalgarh
4. Agreement No.: |  |  | 20/2021-22
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 15/08/2021
7. Stipulated date of Completion: |  |  | 14/08/2022
8. Actual Date of Completion: |  |  | 14/08/2022
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 14/02/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 9699 Date 23-05-2023 |  | SD | 4493
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Arun 22
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Arun Electricals
2. Amount of Deposit: ₹
3. Name of Work: E/f work in Record room at SDM office Kumbhalgarh distt Rajsamand
4. Agreement No.: |  |  | 22/2021-22
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 15/08/2021
7. Stipulated date of Completion: |  |  | 14/05/2022
8. Actual Date of Completion: |  |  | 14/05/2022
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 14/11/2022
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 9700 Date 23-05-2023 |  | SD | 3680
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Arun 23
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Arun Electricals
2. Amount of Deposit: ₹
3. Name of Work: Elect renovation of TB Hospital Building RNT Medical College Udaipur
4. Agreement No.: |  |  | 23/2021-22
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 21/08/2021
7. Stipulated date of Completion: |  |  | 20/08/2022
8. Actual Date of Completion: |  |  | 28/03/2022
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 28/09/2022
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 68461 Date 23-02-2023 |  | SD | 13938
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Arun 25
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Arun Electricals
2. Amount of Deposit: ₹
3. Name of Work: Electric work in College Building at Lasadiya Dist Udaipur
4. Agreement No.: |  |  | 25/2021-22
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 27/08/2021
7. Stipulated date of Completion: |  |  | 26/08/2023
8. Actual Date of Completion: |  |  | 20/08/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 20/02/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 32896 Date 09-12-2023 |  | SD | 131198
Voucher No.- 87896 Date 25-03-2025 |  | SD | 39059
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Arun 37
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Arun Electricals
2. Amount of Deposit: ₹
3. Name of Work: E/F Work in New Govt I.T.I Building at Bhim District Rajsamand
4. Agreement No.: |  |  | 37/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 24/09/2023
7. Stipulated date of Completion: |  |  | 23/03/2025
8. Actual Date of Completion:
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP:
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 76303 Date 25-02-2025 |  | SD | 64129
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Arun 38
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Arun Electricals
2. Amount of Deposit: ₹
3. Name of Work: Electric repair and maintenance work of ward 4,5 and dharamshala T.B Hospital Badi Udaipur
4. Agreement No.: |  |  | 38/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 29/09/2023
7. Stipulated date of Completion: |  |  | 28/02/2024
8. Actual Date of Completion: |  |  | 20/07/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 20/01/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 48866 Date 30-10-2024 |  | SD | 65246
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Arun 40
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Arun Electricals
2. Amount of Deposit: ₹
3. Name of Work: E/F work of Science Faculty in 5 Labs/Hall (physics chemistry Botany Zoology and Maths) with Verandah at Govt Collage Bhim Dist Rajasamand
4. Agreement No.: |  |  | 40/2021-22
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 18/10/2021
7. Stipulated date of Completion: |  |  | 17/04/2023
8. Actual Date of Completion: |  |  | 17/04/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 17/10/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 28213 Date 21-08-2023 |  | SD | 94433
Voucher No.- 79049 Date 29-03-2023 |  | SD | 15449
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Arun 42
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Arun Electricals
2. Amount of Deposit: ₹
3. Name of Work: Electric repair and renovation work of various department at MB Hospital Udaipur
4. Agreement No.: |  |  | 42/2021-22
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 13/11/2021
7. Stipulated date of Completion: |  |  | 12/05/2022
8. Actual Date of Completion: |  |  | 20/07/2022
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 20/01/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 80329 Date 31-03-2023 |  | SD | 7411
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Arun 55
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Arun Electricals
2. Amount of Deposit: ₹
3. Name of Work: Repair of 44 LSQ located in the New Complex Police Station Nathdwara District Rajsamand
4. Agreement No.: |  |  | 55/2021-22
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 16/01/2022
7. Stipulated date of Completion: |  |  | 15/07/2022
8. Actual Date of Completion: |  |  | 21/03/2022
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 21/09/2022
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 41818 Date 11-02-2022 |  | SD | 3523
Voucher No.- 41818 Date 11-02-2022 |  | MD-V | 25000
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Arun 56
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Arun Electricals
2. Amount of Deposit: ₹
3. Name of Work: Electric Repair and Mtc work in Treasury Office Rajsamand
4. Agreement No.: |  |  | 56/2021-22
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 16/01/2022
7. Stipulated date of Completion: |  |  | 15/07/2022
8. Actual Date of Completion: |  |  | 28/03/2022
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 28/09/2022
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 8634 Date 19-05-2022 |  | SD | 2825
Voucher No.- 8634 Date 19-05-2022 |  | MD-V | 70000
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Arun 61
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Arun Electricals
2. Amount of Deposit: ₹
3. Name of Work: E/f work in govt girls College Building at Rajsamand
4. Agreement No.: |  |  | 61/2021-22
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 28/01/2022
7. Stipulated date of Completion: |  |  | 27/10/2022
8. Actual Date of Completion: |  |  | 02/09/2022
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 02/03/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 47713 Date 30-11-2022 |  | SD | 63130
Voucher No.- 47713 Date 30-11-2022 |  | MD-V | 100000
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Arun 62
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Arun Electricals
2. Amount of Deposit: ₹
3. Name of Work: E/F work in 13 Additional Class room at Govt SR.S.econdary School at Kothariya Dist Udaipur
4. Agreement No.: |  |  | 62/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 26/01/2023
7. Stipulated date of Completion: |  |  | 25/11/2023
8. Actual Date of Completion: |  |  | 25/11/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 25/05/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 21891 Date 15-07-2024 |  | SD | 52072
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Arun 67
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Arun Electricals
2. Amount of Deposit: ₹
3. Name of Work: EF work in executive engineer office building at Nathdwara Dist Rajasamand
4. Agreement No.: |  |  | 67/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 18/10/2023
7. Stipulated date of Completion: |  |  | 17/08/2024
8. Actual Date of Completion: |  |  | 10/01/2025
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 10/07/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 92519 Date 31-03-2025 |  | SD | 53070
Voucher No.- 92521 Date 31-03-2025 |  | SD | 9856
Voucher No.- 92520 Date 31-03-2025 |  | SD | 12888
Voucher No.- 92519 Date 31-03-2025 |  | MD-V | 28000
Voucher No.- 92521 Date 31-03-2025 |  | MD-V | 5200
Total: |  | MD-V
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Arun 72
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Arun Electricals
2. Amount of Deposit: ₹
3. Name of Work: E/F Work in Classroom at Kagmadarada Semal Distt Rajsamand
4. Agreement No.: |  |  | 72/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 18/10/2023
7. Stipulated date of Completion: |  |  | 17/10/2024
8. Actual Date of Completion: |  |  | 13/01/2025
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 13/07/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 1564186 Date 21-07-2025 |  | SD | 49508
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Arun 78
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Arun Electricals
2. Amount of Deposit: ₹
3. Name of Work: EF WORK IN APP OFFICE IN ADJ COURT NATHDWARA DISTT. UDAIPUR
4. Agreement No.: |  |  | 78/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 18/10/2023
7. Stipulated date of Completion: |  |  | 17/08/2024
8. Actual Date of Completion: |  |  | 19/06/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 19/12/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 86336 Date 24-03-2025 |  | SD | 21791
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Arun 81
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Arun Electricals
2. Amount of Deposit: ₹
3. Name of Work: E/F Work in Classroom at Govt. SenioR.S.econdary School Parsuniya (Tantol) Nathdwara Distt Rajsamand
4. Agreement No.: |  |  | 81/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 17/12/2023
7. Stipulated date of Completion: |  |  | 16/12/2024
8. Actual Date of Completion: |  |  | 16/12/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 16/06/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 1389822 Date 07-07-2025 |  | SD | 48532
Voucher No.- 1389822 Date 07-07-2025 |  | MD-V | 30000
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Arun 95
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Arun Electricals
2. Amount of Deposit: ₹
3. Name of Work: Elect Rewiring and Various elect works in Circuit House Rajsamand
4. Agreement No.: |  |  | 95/2020-21
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 04/03/2021
7. Stipulated date of Completion: |  |  | 03/09/2021
8. Actual Date of Completion: |  |  | 11/02/2022
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 11/08/2022
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 26170 Date 23-08-2022 |  | SD | 9843
Voucher No.- 77891 Date 27-03-2023 |  | SD | 7182
Voucher No.- 26170 Date 23-08-2022 |  | MD-V | 32329
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Ashapura 130
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Ashapura Electric
2. Amount of Deposit: ₹
3. Name of Work: E/F Work in Police chowki javad district udaipur
4. Agreement No.: |  |  | 130/2015-16
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 14/02/2016
7. Stipulated date of Completion: |  |  | 13/10/2016
8. Actual Date of Completion: |  |  | 08/06/2017
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 08/12/2017
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 24242 Date 08-01-2024 |  | SD | 20073
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## AVON 51
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | AVON ELEVATORS
2. Amount of Deposit: ₹
3. Name of Work: A.M.C. of Elevator in DJ Court in Court Campus, Udaipur
4. Agreement No.: |  |  | 51/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 16/12/2022
7. Stipulated date of Completion: |  |  | 15/05/2023
8. Actual Date of Completion: |  |  | 15/05/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 15/11/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 31436 Date 09-04-2023 |  | SD | 1279
Voucher No.- 37432 Date 10-05-2023 |  | SD | 3235
Voucher No.- 28459 Date 22-08-2023 |  | SD | 2826
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Bajaj 91
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Bajaj Electricals Ltd
2. Amount of Deposit: ₹
3. Name of Work: Electric Lighting work in Block Level Rajiv Gandhi Model Khel Stadium at Tehsil Bhim Dist Rajsamand, FDPAID - 76173
4. Agreement No.: |  |  | 91/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 06/04/2023
7. Stipulated date of Completion: |  |  | 06/10/2023
8. Actual Date of Completion: |  |  | 04/10/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 04/04/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 33381 Date 13-09-2023 |  | SD | 702812
Voucher No.- 48812 Date 30-10-2024 |  | SD | 388703
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Bhawani 09
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Bhawani aiR.S.ystems
2. Amount of Deposit: ₹
3. Name of Work: SITC of AC work in MCH Building Nathdwara Dist Rajsamand
4. Agreement No.: |  |  | 09/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 19/08/2023
7. Stipulated date of Completion: |  |  | 18/02/2024
8. Actual Date of Completion: |  |  | 07/03/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 07/09/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 82237 Date 03-11-2025 |  | SD | 42107
Voucher No.- 81716 Date 29-03-2024 |  | SD | 121676
Voucher No.- 82237 Date 03-11-2025 |  | MD-V | 50000
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur