## Bitu 36
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Bitu Prabhat Electrical
2. Amount of Deposit: ₹
3. Name of Work: Fire Detection and Fire Fighting work in Meeting Hall(Auditorium) at Khamnore Distt Rajsamand
4. Agreement No.: |  |  | 36/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 23/09/2023
7. Stipulated date of Completion: |  |  | 22/03/2024
8. Actual Date of Completion: |  |  | 27/07/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 27/01/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 39518 Date 10-07-2024 |  | SD | 69352
Voucher No.- 1829688 Date 08-11-2025 |  | SD | 61786
Voucher No.- 36052 Date 24-09-2024 |  | SD | 25217
Voucher No.- 1829688 Date 08-11-2025 |  | MD-V | 50000
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## GANPATI 49
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | GANPATI COMMUNICATION SERVICES
2. Amount of Deposit: ₹
3. Name of Work: SITC of DG set and Substation work in Auditorium at Khammnore District Rajasamand
4. Agreement No.: |  |  | 49/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 12/10/2023
7. Stipulated date of Completion: |  |  | 11/04/2024
8. Actual Date of Completion: |  |  | 01/08/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 01/02/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 40568 Date 10-10-2024 |  | SD | 277281
Voucher No.- 86266 Date 24-03-2025 |  | SD | 62104
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## GANPATI 71
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | GANPATI COMMUNICATION SERVICES
2. Amount of Deposit: ₹
3. Name of Work: EF work in Meeting Hall Auditorium at Khamnore dist Udaipur
4. Agreement No.: |  |  | 71/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 04/02/2023
7. Stipulated date of Completion: |  |  | 03/02/2024
8. Actual Date of Completion: |  |  | 01/08/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 01/02/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 52308 Date 12-08-2023 |  | SD | 65501
Voucher No.- 21204 Date 07-11-2024 |  | SD | 205642
Voucher No.- 84115 Date 18-03-2025 |  | SD | 75565
Voucher No.- 55545 Date 22-12-2023 |  | SD | 42891
Voucher No.- 46208 Date 29-10-2024 |  | SD | 113373
Total: |  | MD-V
Voucher No.- 46208 Date 29-10-2024 |  | MD-V | 113373
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Ganpati 18
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Ganpati Engineering and Electricals
2. Amount of Deposit: ₹
3. Name of Work: Remaining LAN Work in SR Hostel at RNT Medical College, Udaipur
4. Agreement No.: |  |  | 18/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 25/09/2022
7. Stipulated date of Completion: |  |  | 24/10/2022
8. Actual Date of Completion: |  |  | 23/10/2022
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 23/04/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 70886 Date 03-01-2023 |  | SD | 19800
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Goyal 07
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Goyal Electricals
2. Amount of Deposit: ₹
3. Name of Work: SITC of 250KVA Transformer work at TAD Commissionar Office Udaipur
4. Agreement No.: |  |  | 07/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 20/08/2023
7. Stipulated date of Completion: |  |  | 19/11/2023
8. Actual Date of Completion: |  |  | 09/02/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 09/08/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 24244 Date 08-01-2024 |  | SD | 19298
Voucher No.- 83427 Date 31-03-2024 |  | SD | 92580
Voucher No.- 83427 Date 31-03-2024 |  | MD-V | 92580
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Gupta 27
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Gupta Electricals
2. Amount of Deposit: ₹
3. Name of Work: Electric renovation of RNT Medical College Udaipur
4. Agreement No.: |  |  | 27/2021-22
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 11/09/2021
7. Stipulated date of Completion: |  |  | 10/09/2022
8. Actual Date of Completion: |  |  | 04/07/2022
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 04/01/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 25490 Date 18-08-2022 |  | SD | 9687
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Gupta 41
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Gupta Electricals
2. Amount of Deposit: ₹
3. Name of Work: E/f work of Science Faculty in 3 Classrooms and 2 Lecture theatre with verandah at Govt. College Bhim Dist. Rajsamand
4. Agreement No.: |  |  | 41/2021-22
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 08/10/2021
7. Stipulated date of Completion: |  |  | 17/01/2023
8. Actual Date of Completion: |  |  | 10/04/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 10/10/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 13247 Date 06-09-2023 |  | SD | 6688
Voucher No.- 57906 Date 16-01-2023 |  | SD | 7903
Voucher No.- 77893 Date 27-03-2023 |  | SD | 5904
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Gupta 43
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Gupta Electricals
2. Amount of Deposit: ₹
3. Name of Work: E/f in Govt College Building Railmagra Rajsamand
4. Agreement No.: |  |  | 43/2021-22
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 11/12/2021
7. Stipulated date of Completion: |  |  | 10/06/2023
8. Actual Date of Completion: |  |  | 10/04/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 10/10/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 13456 Date 06-12-2023 |  | SD | 14382
Voucher No.- 57812 Date 16-01-2023 |  | SD | 33533
Voucher No.- 37542 Date 17-10-2022 |  | SD | 20780
Voucher No.- 20257 Date 20-07-2022 |  | SD | 4993
Voucher No.- 77894 Date 27-03-2023 |  | SD | 15529
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## K3 17
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | K3 Construction Company
2. Amount of Deposit: ₹
3. Name of Work: SITC of 500KVA DG Set with AMF Panel at NEW OPD Block at RNT Medical College Udaipur
4. Agreement No.: |  |  | 17/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 24/09/2022
7. Stipulated date of Completion: |  |  | 23/03/2023
8. Actual Date of Completion: |  |  | 20/03/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 20/09/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 26977 Date 14-08-2023 |  | SD | 178270
Voucher No.- 14203 Date 16-06-2023 |  | SD | 130312
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Kartik 131
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Kartik Traders
2. Amount of Deposit: ₹
3. Name of Work: E/f in Consumer court Circuit Bench court Campus Udaipur
4. Agreement No.: |  |  | 131/2016-17
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 18/03/2017
7. Stipulated date of Completion: |  |  | 17/11/2017
8. Actual Date of Completion: |  |  | 10/03/2018
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 10/09/2018
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 30191 Date 09-12-2022 |  | SD | 1085
Voucher No.- 30192 Date 09-12-2022 |  | SD | 20073
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Kartik 43
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Kartik Traders
2. Amount of Deposit: ₹
3. Name of Work: SITC of ACs in Meeting Hall at SDM office at Kumbhalgarh Distt Rajsamand
4. Agreement No.: |  |  | 43/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 16/01/2023
7. Stipulated date of Completion: |  |  | 31/01/2023
8. Actual Date of Completion: |  |  | 30/01/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 30/07/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 77892 Date 27-03-2023 |  | SD | 3947
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## KHATRI 29
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | KHATRI ELECTRIC SERVICE
2. Amount of Deposit: ₹
3. Name of Work: E/f In Skill Development Canter RNT Medical Collage Udaipur
4. Agreement No.: |  |  | 29/2020-21
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 05/09/2020
7. Stipulated date of Completion: |  |  | 04/03/2022
8. Actual Date of Completion: |  |  | 01/03/2022
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 01/09/2022
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 57888 Date 16-01-2023 |  | SD | 5829
Voucher No.- 57888 Date 16-01-2023 |  | MD-V | 25000
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## KHATRI 45
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | KHATRI ELECTRIC SERVICE
2. Amount of Deposit: ₹
3. Name of Work: Electricfication work in Tahsil Building at Kherwada Dist. Udaipur
4. Agreement No.: |  |  | 45/2021-22
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 02/01/2022
7. Stipulated date of Completion: |  |  | 30/06/2023
8. Actual Date of Completion: |  |  | 20/09/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 20/03/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 39533 Date 10-07-2024 |  | SD | 66598
Voucher No.- 9020 Date 16-05-2023 |  | SD | 11907
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## KHATRI 47
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | KHATRI ELECTRIC SERVICE
2. Amount of Deposit: ₹
3. Name of Work: Electrification work in Divisional and deputy director (rural) SI and GPF office Udaipur
4. Agreement No.: |  |  | 47/2021-22
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 06/01/2022
7. Stipulated date of Completion: |  |  | 05/07/2023
8. Actual Date of Completion: |  |  | 28/08/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 28/02/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 59813 Date 18-12-2024 |  | SD | 8694
Voucher No.- 53297 Date 26-11-2024 |  | SD | 34641
Voucher No.- 53297 Date 26-11-2024 |  | MD-V | 50000
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Krim 117
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Krim Engineering
2. Amount of Deposit: ₹
3. Name of Work: E/f in Ambedker Hostel Nathdwara Rajsamand
4. Agreement No.: |  |  | 117/2017-18
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 26/03/2018
7. Stipulated date of Completion: |  |  | 27/04/2018
8. Actual Date of Completion: |  |  | 26/04/2018
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 26/10/2018
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 66845 Date 15-01-2025 |  | SD | 6407
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## MANDORE 15
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | MANDORE FIRE SAFETY CENTRE
2. Amount of Deposit: ₹
3. Name of Work: AMC of fire fighting system in MBGH campus udaipur fy 2024 & 2025
4. Agreement No.: |  |  | 15/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 05/10/2024
7. Stipulated date of Completion: |  |  | 04/10/2025
8. Actual Date of Completion:
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP:
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 1762759 Date 08-05-2025 |  | SD | 10131
Voucher No.- 1025867 Date 06-10-2025 |  | SD | 10130
Voucher No.- 614057 Date 13-05-2025 |  | SD | 10131
Voucher No.- 67065 Date 15-01-2025 |  | SD | 74658
Voucher No.- 75877 Date 24-02-2025 |  | SD | 10310
Total: |  | SD
Voucher No.- 1198907 Date 26-06-2025 |  | SD | 10131
Voucher No.- 91877 Date 31-03-2025 |  | SD | 41785
Voucher No.- 91877 Date 31-03-2025 |  | MD-V | 50000
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## MANDORE 40
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | MANDORE FIRE SAFETY CENTRE
2. Amount of Deposit: ₹
3. Name of Work: AMC work of fire protection system in SSB at MBGH Udaipur (2022-23)
4. Agreement No.: |  |  | 40/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 12/12/2022
7. Stipulated date of Completion: |  |  | 11/12/2023
8. Actual Date of Completion: |  |  | 11/12/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 11/06/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 31955 Date 09-06-2023 |  | SD | 9032
Voucher No.- 26589 Date 08-10-2023 |  | SD | 17574
Voucher No.- 74958 Date 13-03-2024 |  | SD | 17212
Voucher No.- 48349 Date 21-11-2023 |  | SD | 17212
Voucher No.- 77881 Date 27-03-2023 |  | SD | 2720
Total: |  | SD
Voucher No.- 22623 Date 28-07-2023 |  | SD | 8542
Voucher No.- 22593 Date 28-07-2023 |  | SD | 9032
Voucher No.- 80327 Date 31-03-2023 |  | SD | 2475
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## MANDORE 41
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | MANDORE FIRE SAFETY CENTRE
2. Amount of Deposit: ₹
3. Name of Work: A.M.C. of Fire Fighting System in DJ Court Campus, Udaipur-
4. Agreement No.: |  |  | 41/2022-2023
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 15/12/2022
7. Stipulated date of Completion: |  |  | 14/12/2023
8. Actual Date of Completion: |  |  | 15/05/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 15/11/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 38647 Date 10-11-2023 |  | SD | 13084
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## MANDORE 45
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | MANDORE FIRE SAFETY CENTRE
2. Amount of Deposit: ₹
3. Name of Work: Fire fighting work in satelite hospital at ambamata Udaipur
4. Agreement No.: |  |  | 45/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 12/10/2023
7. Stipulated date of Completion: |  |  | 11/02/2024
8. Actual Date of Completion: |  |  | 10/02/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 10/08/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 20602 Date 07-09-2024 |  | SD | 16479
Voucher No.- 73724 Date 03-11-2024 |  | SD | 33775
Voucher No.- 20602 Date 07-09-2024 |  | MD-V | 50000
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## MANDORE 6
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | MANDORE FIRE SAFETY CENTRE
2. Amount of Deposit: ₹
3. Name of Work: Fire Fighting Work in MCH Building Nathdawara Dist Rajsamand
4. Agreement No.: |  |  | 6/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 08/08/2023
7. Stipulated date of Completion: |  |  | 07/02/2024
8. Actual Date of Completion: |  |  | 10/03/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 10/09/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 55547 Date 22-12-2023 |  | SD | 70480
Voucher No.- 46204 Date 29-10-2024 |  | SD | 133147
Voucher No.- 92522 Date 31-03-2025 |  | SD | 97081
Voucher No.- 92522 Date 31-03-2025 |  | MD-V | 150000
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## MANDORE 69
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | MANDORE FIRE SAFETY CENTRE
2. Amount of Deposit: ₹
3. Name of Work: Annual Operation and Maintenance contract of fire Protection system at MBGH Campus Udaipur(2022-23)
4. Agreement No.: |  |  | 69/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 26/01/2023
7. Stipulated date of Completion: |  |  | 25/01/2024
8. Actual Date of Completion: |  |  | 25/01/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 25/07/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 31956 Date 09-06-2023 |  | SD | 9203
Voucher No.- 26183 Date 08-08-2023 |  | SD | 18685
Voucher No.- 66677 Date 02-09-2024 |  | SD | 9056
Voucher No.- 47163 Date 11-10-2023 |  | SD | 9129
Voucher No.- 48347 Date 21-11-2023 |  | SD | 18853
Total: |  | SD
Voucher No.- 22590 Date 28-07-2023 |  | SD | 9334
Voucher No.- 79810 Date 31-03-2023 |  | SD | 5461
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## MANDORE 78
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | MANDORE FIRE SAFETY CENTRE
2. Amount of Deposit: ₹
3. Name of Work: Fire Fighting Work in 20 nos Quarters For Nursing & Ministerial Staff at MGBH Campus, Udaipur
4. Agreement No.: |  |  | 78/2021-22
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 04/04/2022
7. Stipulated date of Completion: |  |  | 03/07/2022
8. Actual Date of Completion: |  |  | 03/07/2022
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 03/01/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 46282 Date 22-11-2022 |  | SD | 14889
Voucher No.- 46282 Date 22-11-2022 |  | MD-V | 25000
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## MANDORE 94
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | MANDORE FIRE SAFETY CENTRE
2. Amount of Deposit: ₹
3. Name of Work: AMC and opration of fire fighting system at SSB building fire station at MBGH Udaipur
4. Agreement No.: |  |  | 94/2020-21
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 04/03/2021
7. Stipulated date of Completion: |  |  | 03/03/2022
8. Actual Date of Completion: |  |  | 02/04/2022
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 02/10/2022
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 37544 Date 17-10-2022 |  | SD | 3445
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mechanical 57
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mechanical Services
2. Amount of Deposit: ₹
3. Name of Work: SITC of Air conditioner work in meeting hall(Auditorium) at khamnore Distt.-Rajsamand
4. Agreement No.: |  |  | 57/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 12/10/2023
7. Stipulated date of Completion: |  |  | 11/04/2024
8. Actual Date of Completion: |  |  | 04/07/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 04/01/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 16984 Date 24-06-2024 |  | SD | 307834
Voucher No.- 87777 Date 25-03-2025 |  | SD | 234266
Voucher No.- 81217 Date 28-03-2024 |  | SD | 107084
Voucher No.- 87777 Date 25-03-2025 |  | MD-V | 150000
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Metro 03
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Metro International
2. Amount of Deposit: ₹
3. Name of Work: AMC of 3 Nos Passenger Elevator at DJ Court Campus Udaipur(FY 2024-25)
4. Agreement No.: |  |  | 03/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 18/08/2024
7. Stipulated date of Completion: |  |  | 17/05/2025
8. Actual Date of Completion: |  |  | 17/05/2025
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 17/11/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 1762746 Date 08-05-2025 |  | SD | 7247
Voucher No.- 83797 Date 17-03-2025 |  | SD | 18332
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur