## Mitul 46
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹ |  |  | 1207
3. Name of Work: E/f work in 5 nos toilet in Jail building Udaipur
4. Agreement No.: |  |  | 46/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 12/12/2022
7. Stipulated date of Completion: |  |  | 11/03/2023
8. Actual Date of Completion: |  |  | 10/03/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 10/09/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 79944 Date 31-03-2023 |  | SD | 1207
Total: |  |  | 1207
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 47
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹ |  |  | 11079
3. Name of Work: Electric Repair/Renovation Work of Hostel Facility in HCM RIPA Udaipur
4. Agreement No.: |  |  | 47/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 18/01/2025
7. Stipulated date of Completion: |  |  | 17/04/2025
8. Actual Date of Completion: |  |  | 27/03/2025
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 27/09/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 92118 Date 31-03-2025 |  | SD | 11079
Total: |  |  | 11079
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 48
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹ |  |  | 5880
3. Name of Work: Elect Rep and Renovation of Hostel Room in RIPA Udaipur
4. Agreement No.: |  |  | 48/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 12/12/2022
7. Stipulated date of Completion: |  |  | 11/03/2023
8. Actual Date of Completion: |  |  | 10/03/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 10/09/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 80330 Date 31-03-2023 |  | SD | 5880
Total: |  |  | 5880
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 49
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹ |  |  | 275549
3. Name of Work: E/F work in Costruction of SDO & Tehsil Office building Girwa Udaipur
4. Agreement No.: |  |  | 49/2021-22
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 15/01/2022
7. Stipulated date of Completion: |  |  | 15/04/2023
8. Actual Date of Completion: |  |  | 02/04/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 02/10/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 26253 Date 08-10-2023 |  | SD | 74012
Voucher No.- 84099 Date 18-03-2025 |  | SD | 30957
Voucher No.- 59791 Date 24-01-2023 |  | SD | 13882
Voucher No.- 83588 Date 31-03-2024 |  | SD | 78349
Voucher No.- 83588 Date 31-03-2024 |  | MD-V | 78349
Total: |  |  | 275549
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 491
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹ |  |  | 56148
3. Name of Work: Electric repair and motor work in Saheliyon ki Bari, Udaipur
4. Agreement No.: |  |  | 49/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 12/12/2022
7. Stipulated date of Completion: |  |  | 11/01/2023
8. Actual Date of Completion: |  |  | 11/01/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 11/07/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 24681 Date 08-02-2023 |  | SD | 41399
Voucher No.- 57525 Date 01-12-2023 |  | SD | 10197
Voucher No.- 79813 Date 31-03-2023 |  | SD | 4552
Total: |  |  | 56148
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 50
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹ |  |  | 881
3. Name of Work: S/F Conduit pipe in Dy.Director (Rural) SI & GPF Office at Udaipur
4. Agreement No.: |  |  | 50/2021-22
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 15/01/2022
7. Stipulated date of Completion: |  |  | 30/01/2022
8. Actual Date of Completion: |  |  | 28/01/2022
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 28/07/2022
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 37384 Date 17-10-2022 |  | SD | 881
Total: |  |  | 881
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 501
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹ |  |  | 53454
3. Name of Work: Electric Repair Work and Maintenance work at Jyoti Bhawan, Udaipur
4. Agreement No.: |  |  | 50/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 21/01/2025
7. Stipulated date of Completion: |  |  | 20/03/2025
8. Actual Date of Completion: |  |  | 17/03/2025
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 17/09/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 91099 Date 30-03-2025 |  | SD | 24454
Voucher No.- 91099 Date 30-03-2025 |  | MD-V | 29000
Total: |  |  | 53454
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 51
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹ |  |  | 13435
3. Name of Work: Electric Repair Work and Maintenance Work at Dak Bunglow Udaipur
4. Agreement No.: |  |  | 51/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 21/01/2025
7. Stipulated date of Completion: |  |  | 20/03/2025
8. Actual Date of Completion: |  |  | 24/02/2025
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 24/08/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 83764 Date 17-03-2025 |  | SD | 13435
Total: |  |  | 13435
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 52
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹ |  |  | 3393
3. Name of Work: Elect Repair and Mtc work in SP Office Rajsamand 2021-22
4. Agreement No.: |  |  | 52/2021-22
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 15/01/2022
7. Stipulated date of Completion: |  |  | 14/05/2022
8. Actual Date of Completion: |  |  | 30/03/2022
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 30/09/2022
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 15205 Date 21-06-2022 |  | SD | 3393
Total: |  |  | 3393
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 55
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹ |  |  | 7650
3. Name of Work: Electric Repair/ Maintenance work in I&II type Residential Quarters at Udaipur
4. Agreement No.: |  |  | 55/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 12/10/2023
7. Stipulated date of Completion: |  |  | 11/10/2024
8. Actual Date of Completion: |  |  | 11/10/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 11/04/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 26424 Date 08-07-2024 |  | SD | 6700
Voucher No.- 25495 Date 18-08-2022 |  | SD | 905
Voucher No.- 1978410 Date 26-08-2025 |  | SD | 45
Total: |  |  | 7650
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 59
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹ |  |  | 30330
3. Name of Work: Upgradation of CCTV Cameras work in EVM/VVPAT store at Faras Khana in Udaipur
4. Agreement No.: |  |  | 59/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 16/01/2023
7. Stipulated date of Completion: |  |  | 16/03/2023
8. Actual Date of Completion: |  |  | 25/03/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 25/09/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 71410 Date 03-07-2024 |  | SD | 9
Voucher No.- 79819 Date 31-03-2023 |  | SD | 24321
Voucher No.- 79961 Date 31-03-2023 |  | MD-V | 6000
Total: |  |  | 30330
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 68
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹ |  |  | 910
3. Name of Work: Electric repair work in Rural treasury at collectorate office udaipur
4. Agreement No.: |  |  | 68/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 26/01/2023
7. Stipulated date of Completion: |  |  | 25/02/2023
8. Actual Date of Completion: |  |  | 25/02/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 25/08/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 79964 Date 31-03-2023 |  | SD | 910
Total: |  |  | 910
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 69
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹ |  |  | 23618
3. Name of Work: Electric Repair and Maintenance work in Rajnagar Police Thana Building Dist Rajsamand
4. Agreement No.: |  |  | 69/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 18/10/2023
7. Stipulated date of Completion: |  |  | 17/03/2024
8. Actual Date of Completion: |  |  | 13/03/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 13/09/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 80058 Date 27-03-2024 |  | SD | 23618
Total: |  |  | 23618
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 691
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹ |  |  | 48303
3. Name of Work: Electric Repair and Maintenance of Girls Hostel Meera Girls College Udaipur
4. Agreement No.: |  |  | 69/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 15/02/2025
7. Stipulated date of Completion: |  |  | 14/08/2025
8. Actual Date of Completion:
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP:
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 1378244 Date 07-04-2025 |  | SD | 48303
Total: |  |  | 48303
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 73
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹ |  |  | 14120
3. Name of Work: Electric Repair and Maintenance Work at LoweR.S.ubordinate Quarter Building 12th Battalion RAC Debari Udaipur
4. Agreement No.: |  |  | 73/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 15/02/2025
7. Stipulated date of Completion: |  |  | 30/03/2025
8. Actual Date of Completion: |  |  | 21/03/2025
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 21/09/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 91172 Date 30-03-2025 |  | SD | 14120
Total: |  |  | 14120
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 75
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹ |  |  | 1736
3. Name of Work: Electric Repair and Maintenance work in Residence No J1/3, Judge Commercial Court, Udaipur
4. Agreement No.: |  |  | 75/2021-22
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 20/03/2022
7. Stipulated date of Completion: |  |  | 19/04/2022
8. Actual Date of Completion: |  |  | 25/03/2022
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 25/09/2022
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 10401 Date 31-05-2022 |  | SD | 1736
Total: |  |  | 1736
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 76
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹ |  |  | 5449
3. Name of Work: Electric repair and maintenance work in CJM residence at Rajsamand
4. Agreement No.: |  |  | 76/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 19/02/2023
7. Stipulated date of Completion: |  |  | 05/04/2023
8. Actual Date of Completion: |  |  | 26/03/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 26/09/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 32647 Date 09-11-2023 |  | SD | 489
Voucher No.- 22957 Date 27-07-2023 |  | SD | 4960
Total: |  |  | 5449
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 761
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹ |  |  | 1990
3. Name of Work: Electric Repair and Maintenance work in ADR Building of DLSA Rajsamand
4. Agreement No.: |  |  | 76/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 18/10/2023
7. Stipulated date of Completion: |  |  | 17/01/2024
8. Actual Date of Completion: |  |  | 16/01/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 16/07/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 75788 Date 18-03-2024 |  | SD | 1990
Total: |  |  | 1990
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 78
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹ |  |  | 8245
3. Name of Work: Elect. rep. work in Residential Qtr Udaipur
4. Agreement No.: |  |  | 78/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 19/02/2023
7. Stipulated date of Completion: |  |  | 18/03/2023
8. Actual Date of Completion: |  |  | 09/03/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 09/09/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 36799 Date 13-10-2022 |  | SD | 2312
Voucher No.- 57910 Date 16-01-2023 |  | SD | 1529
Voucher No.- 31128 Date 16-09-2022 |  | SD | 2870
Voucher No.- 59457 Date 23-01-2023 |  | SD | 1534
Total: |  |  | 8245
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 8
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹ |  |  | 1439
3. Name of Work: P/f of light luminaire and Electric repair work in old PG hostel (Near Child Hospital) at RNT Medical college Udaipur
4. Agreement No.: |  |  | 8/2021-22
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 09/08/2021
7. Stipulated date of Completion: |  |  | 08/10/2021
8. Actual Date of Completion: |  |  | 10/09/2021
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 10/03/2022
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 4487 Date 28-04-2022 |  | SD | 1439
Total: |  |  | 1439
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 83
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹ |  |  | 45879
3. Name of Work: Electric Repair and Maintenance Work in Excise Department, udaipur
4. Agreement No.: |  |  | 83/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 01/03/2025
7. Stipulated date of Completion: |  |  | 31/03/2025
8. Actual Date of Completion: |  |  | 22/03/2025
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 22/09/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 91822 Date 31-03-2025 |  | SD | 35879
Voucher No.- 91822 Date 31-03-2025 |  | MD-V | 10000
Total: |  |  | 45879
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 88
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹ |  |  | 43707
3. Name of Work: Electric Repair and Maintenance Work in CJ & JM Court Building Kotra Distt. Udaipur
4. Agreement No.: |  |  | 88/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 01/03/2025
7. Stipulated date of Completion: |  |  | 30/03/2025
8. Actual Date of Completion: |  |  | 22/03/2025
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 22/09/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 92209 Date 31-03-2025 |  | SD | 28707
Voucher No.- 92209 Date 31-03-2025 |  | MD-V | 15000
Total: |  |  | 43707
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Mitul 90
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Mitul Enterprises
2. Amount of Deposit: ₹
3. Name of Work: Electric repair work in Non Residential GAD Building Udaipur
4. Agreement No.: |  |  | 90/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 24/03/2023
7. Stipulated date of Completion: |  |  | 30/03/2023
8. Actual Date of Completion: |  |  | 28/03/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 28/09/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 11865 Date 06-01-2022 |  | SD | 4485
Voucher No.- 25479 Date 08-04-2023 |  | SD | 2496
Voucher No.- 13305 Date 06-09-2023 |  | SD | 3183
Voucher No.- 9337 Date 17-05-2023 |  | SD | 249
Voucher No.- 37546 Date 17-10-2022 |  | SD | 2372
Total: |  | SD
Voucher No.- 4170 Date 26-04-2023 |  | SD | 1083
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Neha 08
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Neha Electric
2. Amount of Deposit: ₹ |  |  | 178204
3. Name of Work: E/F work in dev narayan boys 50 Bedded hostel at nathdwara District-Rajsamand
4. Agreement No.: |  |  | 08/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 17/08/2023
7. Stipulated date of Completion: |  |  | 17/05/2024
8. Actual Date of Completion: |  |  | 05/07/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 05/01/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 26886 Date 08-08-2024 |  | SD | 82613
Voucher No.- 73737 Date 03-11-2024 |  | SD | 14450
Voucher No.- 82231 Date 03-11-2025 |  | SD | 47911
Voucher No.- 83269 Date 31-03-2024 |  | SD | 33230
Total: |  |  | 178204
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Neha 102
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Neha Electric
2. Amount of Deposit: ₹ |  |  | 68650
3. Name of Work: E/F Work in One stop center (SAKHI) Building at Rajsamand
4. Agreement No.: |  |  | 102/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 09/04/2023
7. Stipulated date of Completion: |  |  | 08/10/2023
8. Actual Date of Completion: |  |  | 03/01/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 03/07/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 83368 Date 31-03-2024 |  | SD | 38650
Voucher No.- 83368 Date 31-03-2024 |  | MD-V | 30000
Total: |  |  | 68650
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur