## Neha 12
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Neha Electric
2. Amount of Deposit: ₹
3. Name of Work: E/f work in Geography Lab at SRK College at Rajsamand
4. Agreement No.: |  |  | 12/2021-22
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 09/08/2021
7. Stipulated date of Completion: |  |  | 08/06/2022
8. Actual Date of Completion: |  |  | 29/04/2022
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 29/10/2022
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 17987 Date 07-04-2022 |  | SD | 8928
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Neha 13
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Neha Electric
2. Amount of Deposit: ₹
3. Name of Work: E/f work in Tehsildar Residence at Kunwariya Distt Rajsamand
4. Agreement No.: |  |  | 13/2021-22
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 09/08/2021
7. Stipulated date of Completion: |  |  | 08/08/2022
8. Actual Date of Completion: |  |  | 12/12/2022
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 12/06/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 45230 Date 16-11-2022 |  | SD | 4461
Voucher No.- 58487 Date 18-01-2023 |  | SD | 2014
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Neha 15
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Neha Electric
2. Amount of Deposit: ₹
3. Name of Work: E/f work in Residence Quarter Tehsildar at Garbhor Distt Rajsamand
4. Agreement No.: |  |  | 15/2020-21
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 09/07/2020
7. Stipulated date of Completion: |  |  | 08/05/2021
8. Actual Date of Completion: |  |  | 09/03/2021
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 09/09/2021
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 17985 Date 07-04-2022 |  | SD | 24785
Voucher No.- 17986 Date 07-04-2022 |  | SD | 8510
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Neha 27
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Neha Electric
2. Amount of Deposit: ₹
3. Name of Work: E/F Work in Tehsil Building at Khamnore District rajsamand
4. Agreement No.: |  |  | 27/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 16/10/2022
7. Stipulated date of Completion: |  |  | 15/09/2023
8. Actual Date of Completion: |  |  | 11/07/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 11/01/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 71421 Date 03-07-2024 |  | SD | 15238
Voucher No.- 22138 Date 16-07-2024 |  | SD | 72028
Voucher No.- 84100 Date 18-03-2025 |  | SD | 65091
Voucher No.- 84100 Date 18-03-2025 |  | MD-V | 50000
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Neha 37
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Neha Electric
2. Amount of Deposit: ₹
3. Name of Work: EF work in resudence quarter of tehsildar at kumbhalgarh distt. Rajasmand
4. Agreement No.: |  |  | 37/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 02/12/2022
7. Stipulated date of Completion: |  |  | 01/06/2023
8. Actual Date of Completion: |  |  | 01/06/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 01/12/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 48346 Date 21-11-2023 |  | SD | 19710
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Neha 38
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Neha Electric
2. Amount of Deposit: ₹
3. Name of Work: Electrification work in Govt College Building at Khamnore Dist. Rajsamand
4. Agreement No.: |  |  | 38/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 02/12/2022
7. Stipulated date of Completion: |  |  | 01/03/2024
8. Actual Date of Completion: |  |  | 26/07/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 26/01/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 24837 Date 08-03-2023 |  | SD | 66876
Voucher No.- 10399 Date 22-05-2024 |  | SD | 193995
Voucher No.- 48813 Date 30-10-2024 |  | SD | 290779
Voucher No.- 80325 Date 31-03-2023 |  | SD | 6675
Voucher No.- 48813 Date 30-10-2024 |  | MD-V | 150000
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Neha 39
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Neha Electric
2. Amount of Deposit: ₹
3. Name of Work: E/F Work in Sub Tehsil Building at Diwer Distt. Rajsamand
4. Agreement No.: |  |  | 39/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 26/12/2024
7. Stipulated date of Completion: |  |  | 25/12/2025
8. Actual Date of Completion: |  |  | 30/07/2025
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 30/01/2026
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 1829685 Date 08-11-2025 |  | SD | 30849
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Neha 40
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Neha Electric
2. Amount of Deposit: ₹
3. Name of Work: E/F Work in Library Building at SRK College Rajsamand
4. Agreement No.: |  |  | 40/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 17/01/2025
7. Stipulated date of Completion: |  |  | 16/07/2025
8. Actual Date of Completion: |  |  | 16/04/2025
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 16/10/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 1025943 Date 06-10-2025 |  | SD | 15835
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Neha 52
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Neha Electric
2. Amount of Deposit: ₹
3. Name of Work: E/F Work in Development of Chawanda Mata Mandir at Railmagra Distt Rajsamand
4. Agreement No.: |  |  | 52/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 12/10/2023
7. Stipulated date of Completion: |  |  | 11/08/2024
8. Actual Date of Completion: |  |  | 30/12/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 30/06/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 92166 Date 31-03-2025 |  | SD | 46763
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Neha 54
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Neha Electric
2. Amount of Deposit: ₹
3. Name of Work: E/F Work in tehsildar residence quarters at khamnore distt rajsamand
4. Agreement No.: |  |  | 54/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 12/10/2023
7. Stipulated date of Completion: |  |  | 11/04/2024
8. Actual Date of Completion: |  |  | 01/10/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 01/04/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 83804 Date 17-03-2025 |  | SD | 20014
Voucher No.- 83804 Date 17-03-2025 |  | MD-V | 20000
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Neha 55
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Neha Electric
2. Amount of Deposit: ₹
3. Name of Work: Providing and Fixing of LED Light Fixtures in ADJ Court Complex at Nathdwara Dist Rajsamand
4. Agreement No.: |  |  | 55/2022-2023
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 09/01/2023
7. Stipulated date of Completion: |  |  | 09/04/2023
8. Actual Date of Completion: |  |  | 24/02/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 24/08/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 79809 Date 31-03-2023 |  | SD | 3489
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Neha 56
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Neha Electric
2. Amount of Deposit: ₹
3. Name of Work: Electric Repair and Maintenace work in DJ Court Complex at Rajsamand
4. Agreement No.: |  |  | 56/2022-2023
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 09/01/2023
7. Stipulated date of Completion: |  |  | 09/04/2023
8. Actual Date of Completion: |  |  | 24/03/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 24/09/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 79956 Date 31-03-2023 |  | SD | 12001
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Neha 57
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Neha Electric
2. Amount of Deposit: ₹
3. Name of Work: Providing and Fixing of LED Light fixtures in DJ Court Complex at Rajsamand
4. Agreement No.: |  |  | 57/2022-2023
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 09/01/2023
7. Stipulated date of Completion: |  |  | 09/04/2023
8. Actual Date of Completion: |  |  | 17/03/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 17/09/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 79807 Date 31-03-2023 |  | SD | 5986
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Neha 59
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Neha Electric
2. Amount of Deposit: ₹
3. Name of Work: E/F work in Meeting at Tehsil Deogarh Distt. Rajsamand
4. Agreement No.: |  |  | 59/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 16/10/2023
7. Stipulated date of Completion: |  |  | 15/08/2024
8. Actual Date of Completion: |  |  | 15/08/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 15/02/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 46210 Date 29-10-2024 |  | SD | 27213
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Neha 6
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Neha Electric
2. Amount of Deposit: ₹
3. Name of Work: E/f in Govt. Nursing Hostel No 2 at MBGH Badi Campus Udaipur
4. Agreement No.: |  |  | 6/2020-21
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 19/06/2020
7. Stipulated date of Completion: |  |  | 18/12/2021
8. Actual Date of Completion: |  |  | 21/07/2022
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 21/01/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 29726 Date 09-08-2022 |  | SD | 18748
Voucher No.- 29726 Date 09-08-2022 |  | MD-V | 100000
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Neha 64
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Neha Electric
2. Amount of Deposit: ₹
3. Name of Work: E/F work in Judicial residence at Dayal shah Rajsamand
4. Agreement No.: |  |  | 64/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 26/01/2023
7. Stipulated date of Completion: |  |  | 12/03/2023
8. Actual Date of Completion: |  |  | 10/03/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 10/09/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 78595 Date 29-03-2023 |  | SD | 886
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Neha 65
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Neha Electric
2. Amount of Deposit: ₹
3. Name of Work: E/f work in Tehsildar Residence at Devgarh Distt Rajsamand
4. Agreement No.: |  |  | 65/2019-20
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 14/02/2020
7. Stipulated date of Completion: |  |  | 13/11/2020
8. Actual Date of Completion: |  |  | 13/11/2020
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 13/05/2021
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 17984 Date 07-04-2022 |  | SD | 16340
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Neha 651
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Neha Electric
2. Amount of Deposit: ₹
3. Name of Work: E/F work in Staff quarters at Circuit house Rajsamand
4. Agreement No.: |  |  | 65/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 26/01/2023
7. Stipulated date of Completion: |  |  | 12/03/2023
8. Actual Date of Completion: |  |  | 12/03/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 12/09/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 79814 Date 31-03-2023 |  | SD | 5830
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Neha 652
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Neha Electric
2. Amount of Deposit: ₹
3. Name of Work: P&F of New LT Cable at DJ Court Complex at Rajsamand
4. Agreement No.: |  |  | 65/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 15/02/2025
7. Stipulated date of Completion: |  |  | 30/03/2025
8. Actual Date of Completion: |  |  | 06/03/2025
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 06/09/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 83811 Date 17-03-2025 |  | SD | 15005
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Neha 68
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Neha Electric
2. Amount of Deposit: ₹
3. Name of Work: Electric Repair and Maintenance Work at Record Room of DJ Court Complex at Rajsamand
4. Agreement No.: |  |  | 68/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 15/02/2025
7. Stipulated date of Completion: |  |  | 30/03/2025
8. Actual Date of Completion: |  |  | 22/03/2025
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 22/09/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 91097 Date 30-03-2025 |  | SD | 12598
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Neha 70
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Neha Electric
2. Amount of Deposit: ₹
3. Name of Work: EF work in Govt SR.S.econdary School at Sagrun Dist Udaipur
4. Agreement No.: |  |  | 70/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 04/02/2023
7. Stipulated date of Completion: |  |  | 03/12/2023
8. Actual Date of Completion: |  |  | 31/08/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 29/02/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 52314 Date 12-08-2023 |  | SD | 51128
Voucher No.- 66674 Date 02-09-2024 |  | SD | 18036
Voucher No.- 26582 Date 08-10-2023 |  | SD | 28043
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Neha 74
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Neha Electric
2. Amount of Deposit: ₹
3. Name of Work: E/F Work in 4 additional classroom in govt SR.S.ec school bhim distt rajsamand
4. Agreement No.: |  |  | 74/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 18/10/2023
7. Stipulated date of Completion: |  |  | 17/08/2024
8. Actual Date of Completion: |  |  | 17/08/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 17/02/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 50538 Date 11-12-2024 |  | SD | 39531
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Neha 81
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Neha Electric
2. Amount of Deposit: ₹
3. Name of Work: E/M work in SC ST Court at Rajsamand
4. Agreement No.: |  |  | 81/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 13/03/2023
7. Stipulated date of Completion: |  |  | 13/05/2023
8. Actual Date of Completion: |  |  | 26/03/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 26/09/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 79960 Date 31-03-2023 |  | SD | 2830
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Neha 82
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Neha Electric
2. Amount of Deposit: ₹
3. Name of Work: Electric work in Circuit House at Rajsamand
4. Agreement No.: |  |  | 82/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 13/03/2023
7. Stipulated date of Completion: |  |  | 26/04/2023
8. Actual Date of Completion: |  |  | 27/03/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 27/09/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 77612 Date 22-03-2024 |  | SD | 5075
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Neha 83
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Neha Electric
2. Amount of Deposit: ₹
3. Name of Work: E/F Work in Meeting Hall at Heera lal Devpura Govt College Amet District Rajsamand
4. Agreement No.: |  |  | 83/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 13/03/2023
7. Stipulated date of Completion: |  |  | 12/09/2023
8. Actual Date of Completion: |  |  | 15/11/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 15/05/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 66824 Date 15-01-2025 |  | SD | 1615
Voucher No.- 86259 Date 24-03-2025 |  | SD | 17259
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur