## Neha 84
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Neha Electric
2. Amount of Deposit: ₹
3. Name of Work: E/F Work 4 Classroom at Shri Heera Lal Devpura College Amet District Rajsamand
4. Agreement No.: |  |  | 84/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 13/03/2023
7. Stipulated date of Completion: |  |  | 12/09/2023
8. Actual Date of Completion: |  |  | 03/12/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 03/06/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 66829 Date 15-01-2025 |  | SD | 3833
Voucher No.- 86640 Date 24-03-2025 |  | SD | 31323
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Neha 85
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Neha Electric
2. Amount of Deposit: ₹
3. Name of Work: E/F Work in Girl Common room at Shri Heera Lal Devpura College Amet Dist Rajsamand
4. Agreement No.: |  |  | 85/2022-23
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 13/03/2023
7. Stipulated date of Completion: |  |  | 12/09/2023
8. Actual Date of Completion: |  |  | 08/12/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 08/06/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 66826 Date 15-01-2025 |  | SD | 611
Voucher No.- 86641 Date 24-03-2025 |  | SD | 7414
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Omega 3
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Omega Elevators
2. Amount of Deposit: ₹
3. Name of Work: SITC of 10 Passengers Elevator in Nursing Quarters (20 nos) at RNT Medical College, Udaipur
4. Agreement No.: |  |  | 3/2021-22
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 29/07/2021
7. Stipulated date of Completion: |  |  | 28/01/2022
8. Actual Date of Completion: |  |  | 13/06/2022
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 13/12/2022
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 80402 Date 31-03-2023 |  | SD | 14580
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Omega 4
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Omega Elevators
2. Amount of Deposit: ₹
3. Name of Work: SITC of 15 Passengers / stretcher 4 stop Lift for Orthopedic, medical and Surgery wards in MB Hospital Campus, Udaipur
4. Agreement No.: |  |  | 4/2021-22
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 29/07/2021
7. Stipulated date of Completion: |  |  | 28/01/2022
8. Actual Date of Completion: |  |  | 21/07/2022
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 21/01/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 80360 Date 31-03-2023 |  | SD | 17280
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Omega 68
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Omega Elevators
2. Amount of Deposit: ₹
3. Name of Work: SITC of 10 Passengers Elevator in Nursing Quarters (44 nos) at RNT Medical College, Udaipur
4. Agreement No.: |  |  | 68/2021-22
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 27/02/2022
7. Stipulated date of Completion: |  |  | 26/12/2022
8. Actual Date of Completion: |  |  | 26/05/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 26/11/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 57877 Date 16-01-2023 |  | SD | 17295
Voucher No.- 58415 Date 18-01-2023 |  | SD | 23786
Voucher No.- 81215 Date 28-03-2024 |  | SD | 19217
Voucher No.- 81214 Date 28-03-2024 |  | SD | 26429
Voucher No.- 57877 Date 16-01-2023 |  | MD-V | 52625
Total: |  | MD-V
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## ORBIS 49
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | ORBIS ELEVATOR CO LTD
2. Amount of Deposit: ₹
3. Name of Work: SITC of 15 Passenger cum Stretcher Elevator in MBGH Main Porch at RNT Medical College Udaipur and SITC of 10 Passenger Elevator in Administrative Building at RNT Medical College Udaipur
4. Agreement No.: |  |  | 49/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 24/01/2025
7. Stipulated date of Completion: |  |  | 23/07/2025
8. Actual Date of Completion:
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP:
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 1232841 Date 07-01-2025 |  | SD | 128237
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Powertech 36
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Powertech Engineers
2. Amount of Deposit: ₹
3. Name of Work: Various Electric Work in Non Residential Building for Rising Rajasthan Summit 2024 in District Rajsamand
4. Agreement No.: |  |  | 36/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 22/11/2024
7. Stipulated date of Completion: |  |  | 21/12/2024
8. Actual Date of Completion: |  |  | 07/12/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 07/06/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 79285 Date 03-03-2025 |  | SD | 7347
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Powertech 37
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Powertech Engineers
2. Amount of Deposit: ₹
3. Name of Work: Various Electric Work in Residential Building for Rising Rajasthan Summit 2024 in district Rajsamand
4. Agreement No.: |  |  | 37/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 22/11/2024
7. Stipulated date of Completion: |  |  | 21/12/2024
8. Actual Date of Completion: |  |  | 07/12/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 07/06/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 79282 Date 03-03-2025 |  | SD | 1292
Voucher No.- 79284 Date 03-03-2025 |  | SD | 1292
Voucher No.- 79283 Date 03-03-2025 |  | SD | 4595
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Powertech 42
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Powertech Engineers
2. Amount of Deposit: ₹
3. Name of Work: Electric Repair and Maintenance Work in Govt Devnarayan Hostel Rajsamand
4. Agreement No.: |  |  | 42/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 17/01/2025
7. Stipulated date of Completion: |  |  | 16/04/2025
8. Actual Date of Completion: |  |  | 25/03/2025
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 25/09/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 91095 Date 30-03-2025 |  | SD | 7843
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Powertech 66
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Powertech Engineers
2. Amount of Deposit: ₹
3. Name of Work: Electric Upgradation Work at Circuit House Rajsamand
4. Agreement No.: |  |  | 66/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 15/02/2025
7. Stipulated date of Completion: |  |  | 30/03/2025
8. Actual Date of Completion: |  |  | 25/03/2025
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 25/09/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 91106 Date 30-03-2025 |  | SD | 16654
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Powertech 67
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Powertech Engineers
2. Amount of Deposit: ₹
3. Name of Work: Electric Repair and Maintenace work at POCSO Court Rajsamand
4. Agreement No.: |  |  | 67/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 15/02/2025
7. Stipulated date of Completion: |  |  | 30/03/2025
8. Actual Date of Completion: |  |  | 22/03/2025
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 22/09/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 91046 Date 30-03-2025 |  | SD | 8057
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Powertech 71
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Powertech Engineers
2. Amount of Deposit: ₹
3. Name of Work: Electric Repair and Maintenance Work in MACT Court at Rajsamand
4. Agreement No.: |  |  | 71/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 15/02/2025
7. Stipulated date of Completion: |  |  | 30/03/2025
8. Actual Date of Completion: |  |  | 24/03/2025
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 24/09/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 91100 Date 30-03-2025 |  | SD | 1832
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Powertech 89
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Powertech Engineers
2. Amount of Deposit: ₹
3. Name of Work: Various Electric Works in VWDC Centre at Court Complex Rajsamand
4. Agreement No.: |  |  | 89/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 01/03/2025
7. Stipulated date of Completion: |  |  | 30/04/2025
8. Actual Date of Completion: |  |  | 25/03/2025
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 25/09/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 92199 Date 31-03-2025 |  | SD | 1932
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## RC 66
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | RC POWER PROJECT LIMITED
2. Amount of Deposit: ₹
3. Name of Work: SITC of Sound System Stage Drapery and stage lighting system in Auditorium at Khamnore Distt. Rajsamand
4. Agreement No.: |  |  | 66/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 18/10/2023
7. Stipulated date of Completion: |  |  | 17/10/2024
8. Actual Date of Completion:
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP:
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 1523540 Date 17-07-2025 |  | SD | 45213
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Riddhi 01
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Riddhi siddhi Enterprises
2. Amount of Deposit: ₹
3. Name of Work: E/F Work in District Hospital Building at Nathdwara Distt. Rajsamand
4. Agreement No.: |  |  | 01/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 30/06/2024
7. Stipulated date of Completion: |  |  | 29/12/2025
8. Actual Date of Completion:
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP:
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 79888 Date 03-05-2025 |  | SD | 96911
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Sarvoday 25
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Sarvoday Electromart
2. Amount of Deposit: ₹
3. Name of Work: Electric Repair and Maintenance Work of EMRS Community Hall at Kotra Distt. Udaipur
4. Agreement No.: |  |  | 25/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 17/11/2024
7. Stipulated date of Completion: |  |  | 16/05/2025
8. Actual Date of Completion: |  |  | 10/04/2025
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 10/10/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 1781737 Date 08-07-2025 |  | SD | 12973
Voucher No.- 1781737 Date 08-07-2025 |  | MD-V | 10000
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Satguru 89
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Satguru Electricals
2. Amount of Deposit: ₹
3. Name of Work: E/f work in Ayurvedic Hospital Nathdwara Rajsamand
4. Agreement No.: |  |  | 89/2018-19
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 04/03/2019
7. Stipulated date of Completion: |  |  | 03/09/2019
8. Actual Date of Completion: |  |  | 02/12/2019
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 02/06/2020
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 68460 Date 23-02-2023 |  | SD | 37578
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Seema 02
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Seema Electricals
2. Amount of Deposit: ₹
3. Name of Work: Electrical Wiring and Fixture Work in Newly Constructed VWDC Room at DJ Court Campus Udaipur
4. Agreement No.: |  |  | 02/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 07/07/2024
7. Stipulated date of Completion: |  |  | 06/11/2024
8. Actual Date of Completion: |  |  | 02/01/2025
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 02/07/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 91879 Date 31-03-2025 |  | SD | 9383
Voucher No.- 91879 Date 31-03-2025 |  | MD-V | 7000
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Seema 11
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Seema Electricals
2. Amount of Deposit: ₹
3. Name of Work: Electric repair Work in PWD campus at Udaipur
4. Agreement No.: |  |  | 11/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 08/09/2024
7. Stipulated date of Completion: |  |  | 07/11/2024
8. Actual Date of Completion: |  |  | 20/09/2024
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 20/03/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 49620 Date 11-06-2024 |  | SD | 6089
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Seema 14
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Seema Electricals
2. Amount of Deposit: ₹
3. Name of Work: Replacement of faulty change over at 500 KVA DG near pump house in electric work at MBGH udaipur
4. Agreement No.: |  |  | 14/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 25/08/2023
7. Stipulated date of Completion: |  |  | 24/10/2023
8. Actual Date of Completion: |  |  | 20/10/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 20/04/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 71565 Date 03-07-2024 |  | SD | 27760
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Seema 141
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Seema Electricals
2. Amount of Deposit: ₹
3. Name of Work: AMC Work of Window and Split ACs at DJ Court Campus, Udaipur
4. Agreement No.: |  |  | 14/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 08/09/2024
7. Stipulated date of Completion: |  |  | 07/09/2025
8. Actual Date of Completion:
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP:
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 91420 Date 31-03-2025 |  | SD | 4989
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Seema 15
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Seema Electricals
2. Amount of Deposit: ₹
3. Name of Work: Electrical Maintenance work in Main building at MBGH Udaipur
4. Agreement No.: |  |  | 15/2023-24
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 25/08/2023
7. Stipulated date of Completion: |  |  | 24/12/2023
8. Actual Date of Completion: |  |  | 06/11/2023
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 06/05/2024
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 73719 Date 03-11-2024 |  | SD | 23736
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Seema 23
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Seema Electricals
2. Amount of Deposit: ₹
3. Name of Work: E/f work in Lab and ward at Satellite Hospital Hiran Magri Udaipur
4. Agreement No.: |  |  | 23/2020-21
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 15/08/2020
7. Stipulated date of Completion: |  |  | 14/08/2021
8. Actual Date of Completion: |  |  | 28/08/2021
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 28/02/2022
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 75725 Date 20-03-2023 |  | SD | 24095
Voucher No.- 75726 Date 20-03-2023 |  | SD | 6816
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Seema 26
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Seema Electricals
2. Amount of Deposit: ₹
3. Name of Work: Electrification work in Govind Guru Samudayik Bhawan in Rishabhdev Panchayat Samiti, District- Udaipur
4. Agreement No.: |  |  | 26/2021-22
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 11/09/2021
7. Stipulated date of Completion: |  |  | 10/09/2022
8. Actual Date of Completion: |  |  | 05/09/2022
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 05/03/2023
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 59356 Date 20-01-2023 |  | SD | 9363
Voucher No.- 59356 Date 20-01-2023 |  | MD-V | 10000
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Neha 27
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Neha Electric
2. Amount of Deposit: ₹
3. Name of Work: Remaining E/FWork in 4 Classroom at Shri Heera Lal Devpura Govt. College Amet Distt. Rajsamand
4. Agreement No.: |  |  | 27/2024-25
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 15/11/2024
7. Stipulated date of Completion: |  |  | 14/03/2025
8. Actual Date of Completion: |  |  | 09/02/2025
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 09/08/2025
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 3942 Date 22-04-2024 |  | SD | 4734
Voucher No.- 91422 Date 31-03-2025 |  | SD | 9982
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur