## Yashaswini 122
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Yashaswini Enterprises
2. Amount of Deposit: ₹
3. Name of Work: E/f work in Tehsil Building in Garbhor Distt Rajsamand
4. Agreement No.: |  |  | 122/2020-21
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 22/03/2021
7. Stipulated date of Completion: |  |  | 21/06/2022
8. Actual Date of Completion: |  |  | 17/05/2022
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 17/11/2022
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 17769 Date 07-01-2022 |  | SD | 14761
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur

## Yashaswini 56
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Yashaswini Enterprises
2. Amount of Deposit: ₹
3. Name of Work: E/f work in Residence Qtr foR.S.DO At Kotra Distt Udaipur
4. Agreement No.: |  |  | 56/2020/21
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 14/11/2020
7. Stipulated date of Completion: |  |  | 13/11/2021
8. Actual Date of Completion: |  |  | 13/03/2021
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 13/09/2021
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 45231 Date 16-11-2022 |  | SD | 2457
Total:
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on and it stood satisfactory.
3. No Defect found during DLP Period.
4. The final time extension granted upto With/without compensation by the competent authority.
5. The defects pointed out by higher authorities or other authorized authorities during inspection etc have been removed by the contractor and compliance has been refund.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur