## Yashaswini 07
ORDER FOR REFUND OF SECURITY DEPOSIT [RWMF 119]
1. Name of Contractor: | Yashaswini Enterprises
2. Amount of Deposit: ₹ |  |  | 33470
3. Name of Work: Elect work in 20 Nos Qtr for Nursing and Ministerial staff at MBGH Campus Udaipur
4. Agreement No.: |  |  | 07/2020-21
5. Reference for granting refunds:
6. Date of Commencement: |  |  | 19/06/2020
7. Stipulated date of Completion: |  |  | 18/12/2021
8. Actual Date of Completion: |  |  | 18/05/2022
9. MB No.:
10. Date of Payment of final bill:
11. Date of Expiry of 3/6 months/DLP: |  |  | 17/05/2027
12. Was work satisfactory: |  |  | Yes
13. Any tools outstanding against contractor: |  |  | Nil
14. Any recovery due from contractor after payment of final bill: |  |  | Nil
15. Extension of time limit sanctioned vide
16. Assistant Engineer Signature's Recommending refund
17. Accountant's Remarks
18. Details of Security Deposit
Bill Num | MB No. | Ded. Type | Amount (₹)
Voucher No.- 67334 Date 14/03/2022 |  | SD | 9006
Voucher No.- 71802 Date 28/03/2022 |  | SD | 10400
Voucher No.- 62492 Date 24/02/2022 |  | SD | 14064
Total: |  |  | 33470
Certified That:-
1. The Work has been completed as per G-schedule.
2. The work has been inspected by the undersigned as on __________ and it stood satisfactory.
3. No defect found during DLP Period.
4. The final time extension granted upto __________ with/without compensation by the competent authority.
5. The defects pointed out by higher/authorized authorities during inspection etc. have been removed by the contractor and compliance has been done.
Divisional Accountant | Assistant Engineer |  | Executive Engineer
PWD Electric Div.- Udaipur